## admin login
SLNO | MODULE | SUBMODULE | BUG DESCRIPTION | PRIORITY | TEST STATUS | TESTED DATE | COMMENT | DEV STATUS
1) | Admin | Roles | In Roles Details page. 1. Click on Edit Button . 2. Update Role and Click on Update Button. 3. Then Auto Refresh is not happening. | P1 | New | 2022-12-14 |  | In progress
2) | Admin | User | In User Details page . 1. click on Add User Details Button. 2. select Role from dropdown. 3. select office Name from dropdown. 4. Enter Phone Number. 5. Enter Email. 6. Enter FirstName and Lastname. 7. Enter Password. 8. Enter invalid Confirm Password. 9. Click on Save Button. Expected : It should show Error message. Actual : it is showing Success Message. | P1 | Closed | 2022-12-14 |  | fixed
3) | Admin | User | In User Details page . 1. click on Edit Button. 2. Enter Password. 8. Enter invalid Confirm Password. 9. Click on Save Button. Expected : It should show Error message. Actual : it is showing Success Message. | P1 | Closed | 2022-12-14 |  | fixed
4) | Admin | User | 1)Click on edit button and edit user details like email id ,phone number it will not update with new data they showing Same old data | p1 | Closed | 2022-08-11 |  | fixed
5) | Admin | User | 1)Under add user details page in that there is no mandatory symbol for email id text field | p2 | closed | 2022-08-11 |  | fixed
6) | Admin | User | 1)Alignement problem in user details page | p3 | New | 2022-08-11 |  | In progress
7) | Admin | User | 1)click on add user button 2)entered all details and click on save button 3)it showing user did not create error message | p1 | Closed | 2022-08-11 |  | fixed
8) | Admin | Roles | 1)same issue will happen in roles editing page also it will not update they showing same old data | p1 | Closed | 2022-08-11 |  | fixed
9) | Admin | User | 1)under edit user page clear button is not working | p1 | Closed | 2022-08-11 |  | fixed
10) | Admin | Roles | 1)alignement issue roles page | p3 | New | 2022-08-11
11) | Admin | Roles | 1)under editing page clear button is not working | p1 | Closed | 2022-08-11 |  | fixed
12) | Master | Country | 1)under add country details there is mandatory symbol for country code | p3 | closed | 2022-08-11 |  | fixed
13) | Master | District | 1)under add district details there is no mandatory symbol for district code text field | p3 | Closed | 2022-09-11 |  | fixed
3) | master | district | 1) after create the country name ,state name , district name ,taluk name, once approve all the thing it is not displaying proper ascending order in the dropdown list . | p1 | new | 2022-09-12 |  | In progress
14) | Master | Taluk | 1) under taluk details page 2)click on approve button 3)if enter something on remark text field the page is automatically loaded. | p1 | ReOpen | 2022-09-11 |  | fixed
15) | Master | state | 1)under add state page country name drop down is not proper alphabitical order if create new country name. | p1 | new | 2022-09-11 |  | In progress
16) | master | gram | 1)click on add gram under add gram page 2)postal code text field is not displayed proper error message 3)if entered invalid postal code. | p1 | Closed | 2022-09-11 |  | fixed
17) | master | discipline | 1)under add discipline page there is no mandatory symbol for discipline code. | p3 | Closed | 2022-09-11 |  | fixed
18) | master | specilization | 1)without approve the discipline 2)data flow to specilization module under discipline drop down | p1 | ReOpen | 2022-09-11 |  | fixed
19) | master | skillset | 1)click on skillset button under add skillset page 2)skillset text field should not accepted valid skillset 3)it displayed error message | p1 | Closed | 2022-09-11 |  | fixed
20) | master | Durgs | 1)click on drugs 2)under drugs details page there is no proper place holder for strength text field. | p1 | Closed | 2022-11-11 |  | fixed
21) | master | Durgs | 1) click on drugs and click on add durgs button 2)under add durgs page entered all details and click on save button it is showing successful message 3)but data is not showing in home page 4)once refresh the page then it is showing | p1 | Closed | 2022-11-11 |  | fixed
| master | drugs | 1) under add drugs page 2) drug type drop down is not proper alphabitical order. | p1 | new | 2022-09-12 |  | In progress
| master | drugs | 1) under add drugs page 2) drugs name text field is not accepting alphnumeric charcter . | p1 | Closed | 2022-09-12 |  | fixed
22) | master | DiagnosticTest | 1)after update the Diagnostic info 2)dialog box is not closing | p1 | ReOpen | 2022-11-11 |  | fixed
24) | partner | hospital | 1)alinement problem in hospital page | p3 | New | 2022-11-11 |  | fixed
25) | partner | hospital | 1)under hospital details update button is not working. | p1 | New | 2022-11-11 |  | fixed
26) | partner | hospital | 1)under hospital details page if customer. 2) entered invalid phone no. 3) it is not showing proper error message. | p1 | New | 2022-11-11 |  | fixed
27) | partner | hospital | 1)under hospital details page there is no mandatory symbol for GST and pan no. | p1 | New | 2022-11-11 |  | fixed
28) | partner | hospital | 1)under hospital details page if customer. 2) entered invalid postal code. 3) it is not showing proper error message. | p1 | new | 2022-11-11 |  | fixed
29) | partner | hospital | 1) under hospital details page entered all details 2)click save button 3)it is not showing proper message | p2 | new | 2022-11-11 |  | fixed
30) | partner | diagontic | 1)Under add diagontic details there is no mandatory symbol for email id, phone no ,name, code,gst, pan no,network ,type,postal code text field. | p1 | new | 16/11/2022 |  | fixed
31) | partner | diagontic | 1) under diagontic details page 2)if customer is not entered registration number it is not showing proper message . | p1 | new | 16/11/2022 |  | fixed | registration number is optional
32) | partner | diagontic | 1)under add diagontic details page . 2) entered all the valid details into textfeild and click on save button but save button is not working. | p1 | new | 16/11/2022 |  | fixed | I enter all the fields data by entering all the optional and mandatory fields, then it is working.
33) | partner | diagontic | 1)under diagontic details 2)if customer enter character into postal code text field it is accepeted . | p1 | new | 16/11/2022 |  | fixed
34) | partner | diagontic | 1)alinement issue in add diagontic details page. | p3 | new | 16/11/2022 |  | fixed
35) | partner | pharmacy | 1)under add pharmacy details there is no mandatory symbol for 2)name,email id ,reg phone no,code ,category,gst text field . | p1 | new | 15/11/2022 |  | fixed
36) | partner | pharmacy | 1) under add pharmacy details category drop down is not working. | p1 | new | 15/11/2022 |  | fixed
37) | partner | pharmacy | 1)under add pharmacy details branch drop down is not working. | p1 | new | 15/11/2022 |  | fixed
38) | partner | pharmacy | 1)under add pharmacy details phone no text field is accepting character. | p1 | new | 15/11/2022 |  | fixed
39) | partner | pharmacy | 1)alinement issue in pharmacy details page. | p1 | new | 15/11/2022 |  | fixed
40) | partner | pharmacy | 1)under add pharmacy details if customer delete the data it is not allow to edit but it is allow to edit. | p1 | new | 15/11/2022 |  | fixed
41) | partner | pharmacy | 1) under pharmacy details alinement problem in coloum visiblity button. | p1 | new | 15/11/2022 |  | fixed

## hospital admin login
SLNO | MODULE | SUBMODULE | BUG DESCRIPTION | PRIORITY | TEST STATUS | TESTED DATE | Dev Status | COMMENT
1) | partner | assistant | 1)Under add assistant details there is no mandatory symbol for email id text field. | p1 | new | 15/11/2022 | fixed
2) | partner | assistant | 1)under add assistant details there is no mandatory symbol for postal code text field | p1 | new | 15/11/2022 | fixed
3) | partner | assistant | 1) under assistant details page 2)if customer enter invalid postal code it is not showing proper error message . | p1 | new | 15/11/2022 | fixed
4) | partner | assistant | 1)under add assistant details page . 2) entered all the valid details into textfeild and click on save button it is not showing proper message . | p1 | new | 15/11/2022 | fixed | if user entered all the fields (both mandatory and optional) and click hit, then it is working fine.
5) | partner | assistant | 1)under edit assistant details 2)if customer enter invalid postal code it is not showing proper error message | p1 | new | 15/11/2022 | fixed
6) | master | drugs | 1) under add drugs page 2) drugs name text field is not accepting alphnumeric charcter . | p1 | new | 2022-09-12 | fixed
7) | partner | doctor | 1)alinement issue in add doctor details. | p3 | new | 15/11/2022 | fixed
8) | partner | doctor | 1)under add doctor details 2)if customer enter invalid postal code it is not showing error message | p1 | new | 15/11/2022 | fixed
9) | partner | hospital | 1) click on add hospital button. 2) under add hospital page. 2) click on category dropdown spelling mistake in taluk hospital. | p3 | new | 2022-09-12 | in progress
10) | registertation | patient | 1)under add patient there is no mandatory symbol for gender,DOB,postal code textfield. | p3 | new | 16/11/2022 | fixed
11) | registertation | patient | 1)under add patient sum insured text field is accepting charcater. | p1 | new | 16/11/2022 | fixed
12) | registertation | patient | 1)under add patient there is no restrication for sum insured textfield. 2)it is accepted unlimited digits. | p1 | new | 16/11/2022 | fixed
13) | registration | Patient registration | 1) click on patient registration 2) under add patient page 3) click on edit patient button under communication details section . 4) click on country drop down select one country and click on state dropdown it is displaying all country state, district ,taluk, gram . | p1 | new | 15/12/2022 | in progress
14) | task | manual appointment | 1) under paitent registration user is delete the one paitent details ( paitent id -516) after that 2) click on add manual appointment under paitent details 3) click on paitent id text field enter 516 that paitent details is displayed. | p1 | new | 2022-09-11 | In progress | need more clarification
15) | task | manual appointment | 1) spelling mistake in add appointment button | p3 | new | 2022-09-12 | fixed
16) | task | manual appoitment | 1) click on Manual Appointment 2) under Manual Appointment page sentence formations is wrong Appointment Manual Details | p1 | new | 14/12/2022 | fixed
17) | task | manual appoitment | 1) click on Manual Appointment 2) under Manual Appointment page delete button is not working. | p1 | new | 14/12/2022 | fixed
18) | task | manual appoitment phc | 1) click on Manual Appointment approve 2) under Appointment approval 3) click on delete button it is showing one confirmation pop up message 4)if click on yes button it is not working | p1 | new | 14/12/2022 | fixed
19) | task | manual appiontment | 1)click on manual appointment 2) under add appointment without enter PATIENTdetails into text field fix appointment button is working. | p1 | new | 16/12/2022 | in progress
20) | task | manual appointment | 1)click on manual appointment . 2) UNDER add appointment enter PATIENTdetails into text field. 3) click on fix appointment button and it is showing one confirm popup message . 4)click on yes it is navigating to Previous-Records page enter all details click on submit button it is not working and document type,document name validation is not working. | p1 | new | 16/12/2022 | in progress
21) | task | manual appointment | 1)click on manual appointment . 2)UNDER add appointment get patient id text field is accepting all charcter and maximum length is not specified. | p1 | new | 16/12/2022 | in progress
22) | task | manual appointment phc | 1) click on manual appointment phc 2)UNDER addmanual appointment phc get patient id text field is accepting all charcter and maximum length is not specified. | p1 | new | 16/12/2022 | in progress
23) | task | manual appiontment | 1)click on manual appointment phc 2) under add manual appointment phc without enter PATIENTdetails into text field fix appointment button is working. | p1 | new | 16/12/2022 | in progress

## doctor
SLNO | MODULE | SUBMODULE | BUG DESCRIPTION | PRIORITY | TEST STATUS | TESTED DATE | Dev Status | Comment
1) | task | manual appointment approve | 1) click on manual appointment 2) under add manual appointment page 3) click on approve button. 4)Approve Consultation page is select approve time and click on approve button 5) it is approved but it is not auto refreshing once manually refersh the page it is displayed | p1 | new | 16/12/2022 | In progress
2) | task | manual appoitment approve | 1) click on Manual Appointment approve 2) under Appointment approval 3) click on reject button it is showing one confirmation pop up message. 4)if click on yes button it is not working. | p1 | new | 2022-12-12 | In progress
3) | consultation | manual appoitment approve | 1) under consultation 2) click on delete button one confromation popup message is displayed. 3)click on yes button . 4) fuctionality is working but data is not deleted. | p1 | new | 16/12/2022 | In progress